# IMPLEMENTATION GUIDE

For Small EU Organisations

# EXECUTIVE SUMMARY

This guide provides a practical roadmap for small EU organisations to implement AI governance in line with the EU AI Act.

Key obligations for deployers:
- Inventory AI systems
- Apply transparency disclosures
- Maintain human oversight
- Report incidents
- Cooperate with authorities

# PHASE 1: FOUNDATION (Days 1-30)

Week 1: Appoint AI Governance Lead, adopt policy

Week 2: Identify all AI systems, create inventory

Week 3: Classify by risk, assess gaps

Week 4: Communicate policy, conduct training

# PHASE 2: BUILD OUT (Days 31-90)

Month 2: Assess vendors, implement transparency

Month 3: Establish incident procedures, run first review

# PHASE 3: MATURITY (Days 91-180)

Quarterly review cycle, continuous improvement

# COMPLIANCE CHECKLIST

[ ] AI Governance Lead appointed

[ ] Policy adopted and communicated

[ ] All AI systems inventoried

[ ] Systems classified by risk

[ ] Vendor assessments complete

[ ] Transparency disclosures in place

[ ] Human oversight defined

[ ] Incident procedure established

[ ] Staff trained

# KEY PERFORMANCE INDICATORS

Inventory Accuracy: 100% documented

Review Completion: 100% on schedule

Training: 100% staff complete

Incident Response: Within 24 hours

# RESOURCES

EU AI Act: artificialintelligenceact.eu

SME Guide: artificialintelligenceact.eu/small-businesses-guide-to-the-ai-act/